## Group member 1
To-do list
To be completed by: |  | 2025-09-26 |  | Name Theophilus Bassaw
Deadline: |  | 2025-09-26 |  | Date 9/26/2025
Homework 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Create Discord and invite members | 2025-09-16 | 2025-09-16 | 2025-09-16 | 0
100% | Assign Partners | 2025-09-16 | 2025-09-16 | 2025-09-22 | 6 | Took awhile for everyone to join
95% | Create Github repo and invite members | 2025-09-16 | 2025-09-16 | 2025-09-22 | 6 | Took awhile for everyone to join. One didn't join
95% | Create Propositions | 2025-09-16 | 2025-09-22 | 2025-09-22 | 6 | Took awhile for everyone to join. One didn't confirm
95% | Record Group Videos and upload to youtube | 2025-09-22 | 2025-09-25 | 2025-09-26 | 4 | Deadline increased by a day. One didn't participate
95% | Collect homework for submission | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2 | Deadline increased by a day. One didn't submit anything.

## Group member 2
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 3
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 4
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 5
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Group member 6
To-do list
To be completed by: |  |  |  | Name
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning
75% | Preparation
50% | Task a
25% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up